## FP
External Inputs (EI) |  | External Outputs (EO) |  | External Inquiries (EQ) |  | Internal Logical Files (ILF) |  | External Interface Files (EIF)
Input | Count | Output | Count | Inquiry | Count | File | Count | File | Count
New incident ticket from Jira | 1 | Suggested similar incidents | 1 | Search knowledge base | 1 | Incident repository | 1 | Jira/ServiceNow database | 1
User chat query (Slack) | 1 | AI-generated runbook | 1 | View historical incident details | 1 | Runbook database | 1 | Slack platform data | 1
Feedback on AI suggestions | 1 | AI-generated postmortem draft | 1 | View AI performance metrics | 1 | Postmortem records | 1 | LLM API service | 1
Runbook approval/rejection | 1 | Chat assistant response | 1 |  |  | User & role data | 1
Postmortem approval | 1 | Metrics dashboard report | 1 |  |  | AI usage logs | 1
Admin configuration updates | 1
Total EI | 6 | Total EO | 5 | Total EQ | 3 | Total EI | 5 | Total EI | 3
Average | 4 | Average | 5 | Average | 4 | Average | 10 | Average | 7
EI FP | 24 | EO FP | 25 | EQ FP | 12 | EI FP | 50 | EI FP | 21
Unadjusted Function Points (UFP)
Component | FP
EI FP | 24
EO FP | 25
EQ FP | 12
ILF FP | 50
EIF FP | 21
Total UFP | 132
Value Adjustment Factor (VAF)
GSCs | 14
Moderate Influence | 3
Total Degree of Influence | 42
VAF | 1.07
Final Functional Point (FP)
FP | 141.24

## COCOMO
Convert FP to LOC
FP | 141
LOC (Python/Django, 25 LOC/FP) | 3525
KLOC | 3.525
Effort Estimation
a | 3
b | 1.12
c | 2.5
d | 0.35
Effort (PM) | 12.301
Effort (PM) | 12.3
Development Time
Time | 6.0174
Team Size
Team Size | 2.0442
Language/Framework | Python + Django

## Final Estimation Summary
Final Estimation Summary
Metric | Value
Unadjusted FP | 132
VAF | 1.07
Final FP | 141.24
LOC | 3525
KLOC | 3.525
Effort (PM) | 12.3
Development Time | 6.0174
Team Size | 2.0442