## Risk Register
Risk ID | Risk Description | Category | Probability (1–5) | Impact (1–5) | Risk Score (P×I) | Mitigation Strategy | Owner | Status | Risk Level
R1 | LLM service downtime or API unavailability | Technical | 3 | 5 | 15 | • Implement retry logic with exponential backoff for API calls. • Maintain a fallback to a secondary/local LLM model. • Set up uptime monitoring and automated alerts for API health. | Backend Team | Open | High
R2 | Inaccurate AI suggestions or wrong incident matching | Technical | 4 | 4 | 16 | • Continuously improve training data quality and labelling. • Introduce a user feedback loop to retrain models on corrections. • Set a confidence-score threshold below which suggestions are flagged. | ML Team | Open | High
R3 | Data security breach or incident data leak | Security | 3 | 5 | 15 | • Enforce AES-256 encryption at rest and TLS in transit. • Apply role-based access control (RBAC) and least-privilege principles. • Schedule quarterly penetration tests and security audits. | Security Team | Open | High
R4 | Delay in ML model development exceeding schedule | Project Management | 3 | 4 | 12 | • Use Agile sprints with weekly milestone reviews. • Allocate a 10 % buffer in each sprint for unexpected blockers. • Escalate unresolved blockers to the project manager within 48 hours. | Project Manager | Open | Medium
R5 | Poor model performance due to insufficient training data | Technical | 3 | 4 | 12 | • Augment dataset with synthetic incident tickets using controlled templates. • Collect and annotate additional historical tickets from team members. • Retrain models regularly as new resolved tickets accumulate. | ML Team | Open | Medium
R6 | Integration failure with external APIs (Jira / Slack) | External | 3 | 4 | 12 | • Perform full integration testing in a staging environment before release. • Implement graceful error handling and fallback messaging for API failures. • Monitor third-party API status pages and subscribe to outage notifications. | Backend Team | Open | Medium
R7 | Vector database crash or index corruption | Technical | 2 | 5 | 10 | • Schedule nightly automated backups of the vector index. • Run periodic integrity checks on FAISS/Chroma indexes. • Document and test a full disaster-recovery procedure. | DevOps Team | Open | Medium
R8 | Incorrect or hallucinated runbook steps generated by LLM | Quality | 4 | 4 | 16 | • Enforce mandatory human review and approval before any runbook is published. • Add a validation checklist that reviewers must complete before approval. • Log rejected runbooks to retrain the generation model. | Incident Manager | Open | High
R9 | System performance degradation under high concurrent load | Technical | 3 | 4 | 12 | • Conduct load testing with simulated peak traffic before go-live. • Deploy auto-scaling policies on cloud infrastructure. • Profile and optimise slow API endpoints identified in testing. | DevOps Team | Open | Medium
R10 | Unauthorised access to sensitive incident logs | Security | 2 | 5 | 10 | • Enforce multi-factor authentication for all user accounts. • Maintain immutable audit logs for all data access events. • Review and rotate access credentials on a 90-day cycle. | Security Team | Open | Medium
R11 | High and unpredictable cost of LLM API usage | Business | 3 | 3 | 9 | • Set monthly API budget caps and trigger alerts at 80 % utilisation. • Cache frequent queries to reduce redundant API calls. • Evaluate open-source model alternatives for cost reduction. | Project Manager | Open | Medium
R12 | User resistance to adopting the AI-powered system | Organizational | 2 | 3 | 6 | • Run structured onboarding sessions and hands-on demos for engineers. • Collect early feedback through a pilot group and iterate on UX. • Publish clear documentation and FAQs to reduce friction. | Management | Open | Low
R13 | Clustering algorithm producing irrelevant or unstable groupings | Technical | 3 | 3 | 9 | • Tune clustering hyperparameters (e.g., epsilon in DBSCAN) using labelled data. • Validate cluster quality with silhouette scores before triggering runbook generation. • Allow incident managers to manually reassign tickets to correct clusters. | ML Team | Open | Medium
R14 | RAG pipeline returning outdated or irrelevant context | Technical | 3 | 4 | 12 | • Re-index the vector store after every batch of resolved tickets. • Implement a recency-weighted retrieval strategy to prioritise newer incidents. • Display source ticket IDs alongside chat answers so users can verify context. | Backend Team | Open | Medium
R15 | PostgreSQL database failure or data corruption | Technical | 2 | 4 | 8 | • Enable automated daily backups with point-in-time recovery. • Deploy a read replica for high-availability and failover. • Test restoration from backup on a monthly schedule. | DevOps Team | Open | Medium
R16 | Scope creep causing feature overload and timeline slippage | Project Management | 3 | 3 | 9 | • Maintain a formal change-request process for any new features. • Review and freeze scope at the start of each sprint. • Communicate scope boundaries clearly to all stakeholders. | Project Manager | Open | Medium
R17 | Insufficient test coverage leading to undetected bugs at launch | Quality | 3 | 4 | 12 | • Define a minimum 80 % unit-test coverage target enforced in CI/CD. • Conduct end-to-end regression testing before every release. • Perform exploratory testing sessions with at least two team members. | QA Team | Open | Medium
R18 | Embedding model producing low-quality semantic representations | Technical | 2 | 3 | 6 | • Benchmark multiple embedding models on a held-out incident similarity dataset. • Fine-tune the chosen model on domain-specific incident vocabulary. • Monitor retrieval precision metrics and retrain if scores drop below threshold. | ML Team | Open | Low
R19 | Key team member unavailability (illness, attrition) | Project Management | 2 | 4 | 8 | • Cross-train at least two members on each critical module. • Maintain up-to-date documentation so knowledge is not siloed. • Identify backup resources or freelancers who can step in if needed. | Project Manager | Open | Medium
R20 | Non-compliance with data privacy regulations (GDPR / IT Act) | Legal | 2 | 4 | 8 | • Conduct a data privacy impact assessment before processing any real incident data. • Anonymise or pseudonymise ticket data used for ML training. • Review compliance requirements with a legal advisor before deployment. | Legal / Compliance | Open | Medium
R21 | Minor UI bugs affecting usability of the dashboard | Quality | 2 | 2 | 4 | • Log all UI defects in a bug tracker and prioritise by severity. • Schedule a dedicated UI polish sprint before final release. | Frontend Team | Low | Low
R22 | Slow adoption by a small subset of non-technical users | Organizational | 1 | 2 | 2 | • Provide optional self-paced tutorial videos for non-technical users. • Assign a designated point of contact for support queries post-launch. | Management | Low | Low
R23 | Minor inconsistencies in ticket metadata (missing tags) | Operational | 2 | 2 | 4 | • Add validation rules to the ticket submission form for required fields. • Run a one-time data-cleaning script to backfill missing metadata. | Backend Team | Low | Low
R24 | Risk of running the system on outdated library versions | Technical | 1 | 2 | 2 | • Use Dependabot or equivalent to flag outdated dependencies automatically. • Schedule a monthly dependency review and update cycle. | DevOps Team | Rejected | Low
R25 | Risk of poor Wi-Fi connectivity affecting demo performance | Operational | 1 | 1 | 1 | • Prepare an offline demo build with pre-cached responses as a contingency. • Test the demo environment connectivity at least one day before presentation. | Project Manager | Rejected | Low

## Risk Matrix
Impact ↓ / Probability → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5